## Gantt Chart
GANTT CHART
PROJECT TITLE : Finance Tracker
WBS NUMBER | TASK TITLE | TASK TITLE | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  | MARCH |  |  |  | APRIL
|  |  | WEEK-1 | WEEK-2 | WEEK-3 | WEEK-4 | WEEK-1 | WEEK-2 | WEEK-3 | WEEK-4 | WEEK-1 | WEEK-2 | WEEK-3 | WEEK-4 | WEEK-1 | WEEK-2 | WEEK-3 | WEEK-4 | WEEK-1 | WEEK-2 | WEEK-3 | WEEK-4
1 | Define Project Scope | bar: DECEMBER WEEK-1
2 | Conduct Feasibility Study | bar: DECEMBER WEEK-2 to DECEMBER WEEK-3
3 | Create Detailed Project Schedule | bar: DECEMBER WEEK-3
4 | Risk Management Planning | bar: DECEMBER WEEK-4 to JANUARY WEEK-1
5 | Develop Core Features | bar: JANUARY WEEK-2 to FEBRUARY WEEK-4
6 | Conduct Testing | bar: JANUARY WEEK-3 to APRIL WEEK-2
7 | Quality Control | bar: JANUARY WEEK-2 to APRIL WEEK-2
8 | Manage Issues & Bugs | bar: MARCH WEEK-1 to APRIL WEEK-1
9 | Final Deployment | bar: APRIL WEEK-2
10 | Conduct Final Review | bar: APRIL WEEK-3 to APRIL WEEK-4